## Instructions
Instructions |  | Categories of Risk - these are examples of the sorts of risks that might fall into each category
Use this information to help you populate the Risk Management tab. The team and guide should discuss whether any additional information needs to be included. Beginning with the Systems Level Design Review, this document should be actively managed by the team, and discussed at each design review throughout MSD I and MSD II. As you approach the end of MSD II, your overall level of risk should approach, if not reach, 0. |  | Technical | Scope creep, components don't work as expected, team members lack the skills necessary to do the work, as-fabricated parts differ from design, flawed assumptions
|  | Resource | Schedule (e.g.: parts don't come in on time, machine shop is busy), personnel (e.g.: team member gets sick, travels for an interview), cost (e.g.: components cost more than expected, fabrication must be outsourced), facilities (e.g.: specialized piece of equipment fails, lose access to lab)
|  | Safety | Injury to team, injury to end user, damage to equipment
|  | Environmental | Team must dispose of significant excess material, design requires hazardou materials, selecting a low-cost component that could lead to shorter life and the need for additional purchases, design requires purchase of consummable items for end user
|  | Social | Design choices cause harm to a team member or end user based on social issues (e.g.: loss of confidentiality, contradicts local cultures and customs)
Likelihood scale | Severity scale | “Importance Score” (Likelihood x Severity) – use this to guide your preference for a risk management strategy
1 - This cause is unlikely to happen | 1 - The impact on the project is very minor. We will still meet deliverables on time and within budget, but it will cause extra work. | Prevent | Action will be taken to prevent the cause(s) from occurring in the first place.
2 - This cause could conceivably happen | 2 - The impact on the project is noticeable. We will deliver reduced functionality, go over budget, or fail to meet some of our requirements. | Reduce | Action will be taken to reduce the likelihood of the cause and/or the severity of the effect on the project, should the cause occur
3 - This cause is very likely to happen | 3 - The impact on the project is severe. We will not be able to deliver, or what we deliver will not meet the customer's needs. | Transfer | Action will be taken to transfer the risk to something else. Insurance is an example of this. You purchase an insurance policy that contractually binds an insurance company to pay for your loss in the event of accident. This transfers the financial consequences of the accident to someone else. Your car is still a wreck, of course.
|  | Accept | Low importance risks may not justify any action at all. If they happen, you simply accept the consequences.

## Risk Management
Team #: | P00000 | Team Name: | Sample MSD Project
Date: | 2015-08-05 11:43 | Document Owner: | Team Member
Revision #: | 1
ID | Category | Risk Item | Effect | Cause | Likelihood | Severity | Importance | Action to Minimize Risk | Owner
| What type of risk is this? | Describe the risk briefly | What is the effect on any or all of the project deliverables if the cause actually happens? | What are the possible cause(s) of this risk? | L | S | L*S | What action(s) will you take (and by when) to prevent, reduce the impact of, and/or transfer the risk of this occurring? | Who is responsible for following through on mitigation?
1 | [6 empty] | 0
2 | [6 empty] | 0
3 | [6 empty] | 0
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0